## Sheet1
GOALS | DESCRIPTION | ESTIMATED TIME | EXPECTED MILESTONE | STATUS | PRIORITY (1-LOWEST TO 10- HIGHEST)
1 | Setting up the database in using room. The tables required are pictures of recipes, recipes, user, preferences. | 5 Hours | Milestone 3 & 4 | IN-PROGRESS | 10
SUBTASK 1 | Users have an id, email field, and a password field. | 15 Minutes | Milestone 3 | DONE | 9
SUBTASK 2 | Recipes have the following fields: ingredients, instructions, title and userId. | 15 Minutes | Milestone 3 | DONE | 9
SUBTASK 3 | Preferences have the following fields:[UserId, PK], Dietary Restrictions, Mealtypes, Cuisine types. | 15 Minutes | Milestone 3 | DONE | 9
2 | Integrate OpenAI API to generate recipe recommendations based on user preferences by injecting it into a prompt. | 4 Hours | Milestone 3 & 4 | IN-PROGRESS | 10
3 | Link database entries with recipe details and images onto the recipe screen using database entries that were created from the AI. | 2 Hours | Milestone 4 | INCOMPLETE | 7
4 | Design a form screen to collect and save user preferences to the database. | 2 Hour | Milestone 3 & 4 | IN-PROGRESS | 6
SUBTASK 4 | Design a form screen to display preference options to the user. | 25 Minutes | Milestone 3 | DONE | 5
5 | Implement login functionality with email and password verification. | 1 Hour | Milestone 3 | DONE | 4
6 | A user gets stored in the database after clicking the registration button. | 1 Hour | Milestone 3 | DONE | 7
7 | Design a Profile screen displaying email, buttons, and profile picture options. | 25 Minutes | Milestone 3 & 4 | IN-PROGRESS | 3
8 | Create user-friendly login interface. | 25 Minutes | Milestone 3 | DONE | 3
9 | Create user-friendly registration interface for the registration screen. | 25 Minutes | Milestone 3 | DONE | 3
10 | Display detailed recipe information from the database on the recipe screen. | 45 Minutes | Milestone 4 | INCOMPLETE | 4
11 | Design consistent navigation using the provider pattern. That smoothly connects each screen. Which contains a navHost, navController and navGraph. | 1 Hour and 30 Minutes | Milestone 3 | DONE | 8
SUBTASK 5 | Create a route thats specific for each screen and connecting the needed parameters for each screen with the route. | 1 Hour | Milestone 3 | DONE | 8
12 | Create a user friendly home screen with buttons for registration and login. | 30 Minutes | Milestone 3 | DONE | 2
13 | Add Scaffold UI with a top bar showing the app's name. | 30 Minutes | Milestone 3 | DONE | 3
14 | A back button allowing for the users to go back to the previous screen. | 40 Minutes | Milestone 3 | DONE | 3
15 | Create settings screen for toggling dark mode and editing preferences. | 45 Minutes | Milestone 3 | DONE | 5
16 | Setting up material theme inside of the app, adding typography, color schemes(light, dark). | 45 Minutes | Milestone 3 | DONE | 6